Driving a Marketing Vision Using Project Management
Session SMS01
Alex S. Brown, PMP
Mitsui Sumitomo Insurance Group, USA

---
Presentation Overview
Case study of MSIG USA
Developed a Marketing Plan
Began executing the plan
Key lessons learned
  - Partnership possible with Marketing and project management
  - Shared focus on deliverables
  - Use Marketing language

---
About MSIG USA
400-person US division of Mitsui Sumitomo Insurance of Japan
Little experience with traditional marketing
Strong brand among Japanese customers
Appointed a Chief Marketing Officer
Using project management to drive strategic initiatives

---
About Alex S. Brown
Almost 15 years experience in project management for financial services companies
Manager of Strategic Planning Office at MSIG USA
Mentor project managers and set PM policies
Participated in the marketing project teams as a team member and mentor

---
Marketing Plan Project
Develop a plan for future marketing activities
Managed by Chief Marketing Officer
Senior management interested and involved
Developed a list of marketing projects
Prioritized the list with executives
Managed using existing PM and strategic planning processes

---
How to Plan the Project?
Had debate over how to organize the plan
Decided on deliverable-oriented approach
Organized work by the chapter headings in the final report
Used marketing terms
Decided against IT-based phased
plan

---
Focus on Deliverables

---
Benefits of Organizing by Deliverables
Focused team on each step
Deadlines easy to see
Progress easy to monitor
Phases would have all finished together at the end
Periodic review and approval
Marketing professionals understood the terms
Helped focus on planning and brainstorming, not immediately executing each new idea

---
Outcome of Marketing Plan Project
Fifteen (15) different ideas for new projects
Prioritized list with a multi-year plan
Few areas of disagreement
Executive sign-off on the projects and their priorities
Focused staff and executives on a few,
initial goals

---
Initial Marketing Projects
Marketing Campaign
  - Set sales goals and monitor results
  - Typical marketing activity, but first time in many years for MSIG USA
  - Adapted for Japanese and US staff
Competitive Analysis
  - Understand competitors and MSIG USA unique selling points
  - Foundation for many other marketing projects

---
Organizing Marketing Projects
Both used marketing terms throughout
Campaign organized by time
  - Preparation work
  - Monthly milestones, reports, and checkpoints
  - Make it “normal business” at the end
Analysis organized by deliverable
  - Used chapter headings in WBS
  - Focused on completing each portion of the analysis
  - Very similar to Marketing Plan project

---
Focus on Communication
Marketing Campaign planned many forms of communications about goals and results
  - E-mail
  - Posters
  - Meetings
Ultimately these were the most important factor cited by senior management
Repeated the campaign to improve communication

---
Reporting Progress
Competitive Analysis needed many sign-offs
Team discussed each chapter in detail
Team faced delays getting the final product ready for executive review
PM discipline lead to success
  - Committed to schedule and scope
  - Had to report on progress frequently
  - Would not be ignored or forgotten – it was on the list

---
Some Decisions Not to Proceed
Some projects never started
Some projects canceled
Corporate Branding
  - Investigated options
  - Found vendors, got quotes
  - Decided price was too high now
Not “failed” projects

---
When Projects Do Not Achieve Planned Results
Abandon projects for good business reasons
Investigate opportunities
  - Some worth pursuing, some not
  - Always a learning experience
Learned to accept “failure”
Some projects will fail, especially when
  - Taking risks
  - Trying something new
Record lessons learned for ALL projects

---
Importance of Documentation
Many marketers resisted documentation and planning
During execution, they learned to appreciate it
Senior executives understood goals and progress
Helped to keep executive support
Many projects closed with documentation
  - Procedures to guide future marketing practices
  - Valuable research reports or proposals

---
Plans Change...
Marketing is unpredictable and creative
Planning practices must adapt for a high-risk, high-change environment
Create plans, realizing they will change
Rapid, team-driven change control
Appropriate levels of sign-off
Quick decisions
Planning still valuable, despite the changes

---
Key Lessons Learned
Marketing can be planned and managed
Marketing and Project Management belong together
Deliverable-oriented plans using marketing terms
Accept failure
Make documentation an asset
Prepare for frequent change

---
Driving a Marketing Vision Using Project Management
Session SMS01
Alex S. Brown, PMP
Mitsui Sumitomo Insurance Group, USA
alexsbrown@alexsbrown.com
http://www.alexsbrown.com/
Clip art and photos from stock.xchng. Thanks to photographers:
Sanja Gjenero (lusi), Ove Tøpfer (topfer), Elvis Santana (tome213), Willi Heidelbach (wilhei66), Stefanie L. (scyza), Davide Guglielmo (brokenarts)